## Sheet1
Issue Summary | Issue Type | Resolved? | Detail | Comment
Multiple Client's have slight difference in Title | Bugfix | Yes | Consider two clients A and B that both run Bluestack app players. The title of A's application is called BlueStacks App Player. The title of B's application is called Bluestacks App Player. There's a slight difference between the two titles; Client A has a capital s and client B has a lowercase s. This discrepency causes the bot to not recognize the application if ran on both client A and B. Please fix so that the bot works in both client A and client B's cases.
We need sort function on ally. | Feature Request | Yes | In the Ally menu, there are two types of sorts: by Attack type (i.e. by melee, missile, and magic) and by power (i.e. ground, air, sea). We need the bot method to be able to sort the ally list by these categories.
Sort allies, but remove filters if none are found | Feature Request | Yes | Would like a feature that adds to the sort allies feature. If an ally is not found, we'd like to remove the TYPE filter and see choose whichever ally is available.
Need a feature that can do quest progression | Feature Request | Yes | Need to be able to progress through the quest scenarios.
First Unit's cost is too high, cannot deploy unit | Bugfix | Yes | Usually the script deploys the first unit. Some quests's max unit points is less than the cost of the first unit, so the script will attempt to deploy the first unit, but it never will be able to do that. | Made it so that the script will pick any of the 4 units when possible instead of just the first unit
Bot stopped responding at unit selection page | Bugfix | Yes | Bot just stops at the unit selection page.
Script doesn't work for screen size 1102 by 677 | Bugfix | Yes | Need to make script work for that screen size
Need to support 632 by 1030 | Feature Request
After Deploy 1 unit, bot just sits there | Bugfix
Bot needs to retry failed quests | Feature Request |  | Edit the BotAllQuests.ahk

## 2151104
Issue Summary | Issue Type | Resolved? | Detail | Comment
Deploy ally makes game stuck | Bugfix |  | When there is not enough allies, the bot clicks the next page but it gets to the last page and still tries to find the next page button, but I can't. so it gets stuck

## 20151105
Issue Summary | Issue Type | Resolved? | Detail | Comment
Add script for Frontlines Event | Feature Request | Yes | Want to automated the frontlines event.
Add support for screen size of 632 by 1030 | Feature Request

## 20160109
Issue Summary | Issue Type | Resolved? | Detail | Comment
Implement fires of perdition event for 632_1030 | Feature Request |  | Obtain resources and write the script code to perform all aspects of the event
Implement fires of perdition event for 677_1102 | Feature Request |  | Obtain resources and write the script code to perform all aspects of the event
Implement fires of perdition event for 1282_749 | Feature Request |  | Obtain resources and write the script code to perform all aspects of the event